## Sheet1
| 2022-08-29 | 5-Sept | 12-Sept | 19-Sept | 26-Sept | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28
Order new Inverter and Converter parts
Design and order PCB for Rectifier
Rebuild Inverter | [5 empty] | 2022-11-21: Completed
Research on Battery Health and Life | [5 empty] | 2022-11-21: In Progress
Rebuild Converter | [5 empty] | 2022-11-21: Behind Schedule
Redesign controller circuits and switching schematic | [5 empty] | 2022-11-21: Not Yet Started
Design Schematics for Buck-Boost Converter
Design and order PCB for Buck-Boost Converter
Design and order PCB for Converter
Design and order PCB for Inverter
Implementation of new Sensors and Health Monitoring
Design and order PCB for controller circuits
Update Presentation 1
Validations for controller switching circuits
Update Presentation 2
Integrate rectifier with buck-boost converter | bar: 2022-10-03
Integrate Inverter with outlet load | bar: 2022-10-03
Sensor testing and working on code | bar: 2022-10-03
Update Presentation 3 | bar: 2022-10-03
Integrate converter with switch controller 1 | bar: 2022-10-03 to 2022-10-17
Improvements to website and data management | bar: 2022-10-10 to 2022-10-31
Integrate switch controller 2 with inverter and converter | bar: 2022-10-03 to 2022-10-17
Update Presentation 4 | bar: 2022-10-17
Update Presentation 5 | bar: 2022-10-31
Final Integration and Validation | bar: 2022-10-24 to 2022-11-14
Final Presentation | bar: 2022-11-14
Final Report | bar: 2022-11-14 to 2022-11-28
Final Demo | bar: 2022-11-28